## Sheet1
| Scope | Story ID | Feature ID / Epic ID | Feature / Epic | Feature / Function / Screen | Type (MoSCoW) / Labels | Impact / Business Value | Dependencies
1 | Yes | S1.1 | E1 | Student Registration | Student Sign-up (Email ) | Must-have | User onboarding entry point | -
2 | Yes | S1.2 | E1 | Student Registration | Profile Setup (Basic Info: Name, College, Degree) | Must-have | Structured identity creation | S1.1
3 | Yes | S1.3 | E1 | Student Registration | Skills & Interests Selection | Must-have | Enables personalization | S1.2
4 | Yes | S1.4 | E1 | Student Registration | Career Goal Selection (Domain preference) | Must-have | Drives roadmap + recommendations | S1.2
5 | Yes | S1.5 | E1 | Student Registration | Profile Dashboard (View/Edit Profile) | Must-have | Central control for user | S1.2
|  | Story ID | Feature ID / Epic ID | Feature / Epic | Feature / Function / Screen | Type (MoSCoW) / Labels | Impact / Business Value | Dependencies
6 | Yes | S2.1 | E2 | Portfolio Management (Builder) | Add Project (Title, Description, Tech Stack) | Must-have | Core portfolio creation and skill demonstration | E1
7 | Yes | S2.2 | E2 | Portfolio Management (Builder) | Add External Links (GitHub, Live URL, Docs) | Must-have | Enhances credibility and proof of work | S2.1
8 | Yes | S2.3 | E2 | Portfolio Management (Builder) | Upload Media (Images, Screenshots) | Must-have | Visual proof increases portfolio impact | S2.1
9 | Yes | S2.4 | E2 | Portfolio Management (Builder) | Add Skills & Certifications | Must-have | Strengthens profile completeness and trust | E1
10 | Yes | S2.5 | E2 | Portfolio Management (Builder) | Tag Project to Tech/Domain Stack & Roadmap items | Must-have | Enables skill mapping and analysis | E5
11 | Yes | S2.6 | E2 | Portfolio Management (Builder) | Edit/Delete Portfolio Entries | Must-have | Ensures data accuracy and control | S2.1
12 | Yes | S2.8 | E2 | Portfolio Management (Builder) | Project Detail View Page | Must-have | Structured display for each project | S2.1
13 | Yes | S2.10 | E2 | Portfolio Management (Builder) | Portfolio Completeness Indicator (%) | Must-have | Encourages users to improve profile | S2.7
|  | Story ID | Feature ID / Epic ID | Feature / Epic | Feature / Function / Screen | Type (MoSCoW) / Labels | Impact / Business Value | Dependencies
14 | Yes | S3.1 | E3 | Portfolio Analysis | Portfolio Data Aggregation (Projects, Skills, Certifications) | Must-have | Consolidates all inputs for analysis | E2
15 | Yes | S3.2 | E3 | Portfolio Analysis | Skill Mapping to Selected Tech/Domain Stack | Must-have | Aligns user profile with career path | E2, E5
16 | Yes | S3.3 | E3 | Portfolio Analysis | Job Readiness Score Calculation Engine (Core Logic) | Must-have | Quantifies employability in a single metric | S3.1, S3.2
17 | Yes | S3.4 | E3 | Portfolio Analysis | Weightage Configuration (Skills, Projects, Certifications) | Must-have | Enables flexible and scalable scoring model | S3.3
| No | S3.5 | E3 | Portfolio Analysis | Gap Analysis (Missing Skills / Weak Areas) | Could-have | Identifies improvement areas clearly | S3.2, S3.3
18 | Yes | S3.6 | E3 | Portfolio Analysis | Strength Analysis (Top Skills / Strong Areas) | Must-have | Builds confidence and highlights strengths | S3.2
| No | S3.7 | E3 | Portfolio Analysis | Project Depth Analysis (Basic vs Advanced Work) | Could-have | Differentiates surface vs deep learning | S3.1
19 | Yes | S3.8 | E3 | Portfolio Analysis | Trend Alignment Check (Profile vs Market Demand) | Must-have | Ensures relevance to current job market | E7
20 | Yes | S3.9 | E3 | Portfolio Analysis | Job Readiness Score Dashboard (UI) | Must-have | Clear visualization of readiness and insights | S3.3
21 | Yes | S3.10 | E3 | Portfolio Analysis | Detailed Insights Panel (Breakdown of Score) | Must-have | Transparency in scoring system | S3.9
| No | S3.11 | E3 | Portfolio Analysis | Improvement Suggestions Engine | Could-have | Drives actionable next steps | S3.5
| No | S3.12 | E3 | Portfolio Analysis | Recommendation Trigger (Feeds Roadmap Engine) | Could-have | Connects analysis to execution | E8
22 | Yes | S3.13 | E3 | Portfolio Analysis | Historical Score Tracking (Progress Over Time) | Must-have | Measures improvement and growth | S3.3
23 | Yes | S3.14 | E3 | Portfolio Analysis | Readiness Level Classification (Beginner / Intermediate / Job-ready) | Must-have | Simplifies understanding for users | S3.3
| No | S3.15 | E3 | Portfolio Analysis | Alerts for Critical Gaps (Missing Core Skills) | Could-have | Prevents blind spots in preparation | S3.5
|  | Story ID | Feature ID / Epic ID | Feature / Epic | Feature / Function / Screen | Type (MoSCoW) / Labels | Impact / Business Value | Dependencies
24 | Yes | S4.1 | E4 | Tech/Domain Definition Engine | Domain Master Setup (Admin Panel – Create/Edit/Delete Domain) | Must-have | Foundation for structured career pathways | -
25 | Yes | S4.2 | E4 | Tech/Domain Definition Engine | Domain Categorization (Tech / Non-Tech / Hybrid) | Must-have | Better classification and scalability | S4.1
26 | Yes | S4.3 | E4 | Tech/Domain Definition Engine | Skill Mapping per Domain (Core + Optional Skills) | Must-have | Defines learning structure for each domain | S4.1
27 | Yes | S4.4 | E4 | Tech/Domain Definition Engine | Role Mapping per Domain (e.g., Frontend Dev, Data Analyst) | Must-have | Connects domains to real job roles | S4.1
28 | Yes | S4.5 | E4 | Tech/Domain Definition Engine | Domain Description & Overview (Scope, Use Cases) | Must-have | Helps students understand domain relevance | S4.1
29 | Yes | S4.6 | E4 | Tech/Domain Definition Engine | Domain Selection UI (Student Side) | Must-have | Entry point for personalization | E1
30 | Yes | S4.7 | E4 | Tech/Domain Definition Engine | Domain Detail View (Skills, Roles, Overview) | Must-have | Informs decision-making for students | S4.3, S4.4
31 | Yes | S4.8 | E4 | Tech/Domain Definition Engine | Multiple Domain Selection Support | Must-have | Enables flexibility in career exploration | S4.6
32 | Yes | S4.9 | E4 | Tech/Domain Definition Engine | Domain Prioritization (Primary vs Secondary) | Must-have | Helps focus and roadmap alignment | S4.8
33 | Yes | S4.10 | E4 | Tech/Domain Definition Engine | Domain Update / Change Flow | Must-have | Allows users to pivot career direction | S4.6
34 | Yes | S4.11 | E4 | Tech/Domain Definition Engine | Domain-to-Trend Mapping (Link with Trend Engine) | Must-have | Enables dynamic updates based on market demand | E7
35 | Yes | S4.12 | E4 | Tech/Domain Definition Engine | Domain-to-Roadmap Mapping | Must-have | Drives roadmap generation logic | E8
36 | Yes | S4.13 | E4 | Tech/Domain Definition Engine | Domain Visibility Control (Active/Inactive Domains) | Must-have | Admin control over offerings | S4.1
37 | Yes | S4.14 | E4 | Tech/Domain Definition Engine | Domain Analytics (Adoption, Popularity) | Must-have | Helps optimize domain offerings | E1, E7
|  | Story ID | Feature ID / Epic ID | Feature / Epic | Feature / Function / Screen | Type (MoSCoW) / Labels | Impact / Business Value | Dependencies
| No | S5.1 | E5 | Tech/Domain Stack Selection & Management | Suggested Stack List based on Trend Analysis and User Profile | Could-have | Reduces confusion and helps students start with relevant stack options | E4
38 | Yes | S5.3 | E5 | Tech/Domain Stack Selection & Management | Stack Selection - Multiple | Must-have | Establishes clear student focus and enables roadmap generation | S5.1
39 | Yes | S5.2 | E5 | Tech/Domain Stack Selection & Management | Stack Detail View (Overview, Skills, Tools, Career Roles) | Must-have | Improves student understanding before making stack choice | S5.1
40 | Yes | S5.7 | E5 | Tech/Domain Stack Selection & Management | Stack Tracking (Selected, In Progress, Completed) | Must-have | Enables measurable progress tracking across chosen stack(s) | S5.6
41 | Yes | S5.11 | E5 | Tech/Domain Stack Selection & Management | Stack-to-Roadmap Mapping | Must-have | Connects stack choice directly to roadmap generation | E8
|  | Story ID | Feature ID / Epic ID | Feature / Epic | Feature / Function / Screen | Type (MoSCoW) / Labels | Impact / Business Value | Dependencies
| No | S6.1 | E6 | Job Feed (System) | Job Data Ingestion (API / Scraper / Manual Upload) | could-have | Ensures continuous inflow of job data for platform intelligence | -
| No | S6.2 | E6 | Job Feed (System) | Job Data Normalization & Cleaning | could-have | Standardizes job data for accurate processing and analysis | S6.1
| No | S6.3 | E6 | Job Feed (System) | Job Classification (Role, Domain, Skills Mapping) | could-have | Enables structured categorization for trends and matching | S6.2, E4
| No | S6.4 | E6 | Job Feed (System) | Entry-Level Job Filtering (0–3 Years Experience) | could-have | Keeps platform focused on fresh graduates | S6.2
42 | Yes | S6.5 | E6 | Job Feed (System) | Job Repository / Storage - Admin manul job management | Must-have | Central database for all job records | S6.2
| No | S6.6 | E6 | Job Feed (System) | Job Feed UI (Student View – List Page) | could-have | Enables students to explore opportunities | S6.5
43 | Yes | S6.7 | E6 | Job Feed (System) | Job Detail View (Description, Skills, Company, Apply Link) | Must-have | Provides complete information for decision-making | S6.6
44 | Yes | S6.8 | E6 | Job Feed (System) | Job Filters (Domain, Skills, Location, Role) | Must-have | Improves usability and relevance of job discovery | S6.6
| No | S6.9 | E6 | Job Feed (System) | Search Functionality (Keyword-based Search) | Could-have | Enhances accessibility of job listings | S6.6
| No | S6.10 | E6 | Job Feed (System) | Job Save / Bookmark Feature | Must-have | Improves engagement and tracking of opportunities | S6.6
| NO | S6.11 | E6 | Job Feed (System) | Apply Redirect (External Application Link Handling) | Must-have | Enables seamless application flow | S6.7
| No | S6.12 | E6 | Job Feed (System) | Job Expiry & Status Management | Must-have | Maintains relevance and data freshness | S6.5
| No | S6.13 | E6 | Job Feed (System) | Duplicate Job Detection & Removal | Must-have | Ensures clean and reliable job feed | S6.2
45 | Yes | S6.14 | E6 | Job Feed (System) | Job Feed Integration with Trend Engine | Must-have | Feeds real-time data into trend analysis system | E7
| No | S6.15 | E6 | Job Feed (System) | Job Feed Personalization (Basic – based on Domain/Stack) | Must-have | Improves relevance for users without full AI engine | E1, E5
|  | Story ID | Feature ID / Epic ID | Feature / Epic | Feature / Function / Screen | Type (MoSCoW) / Labels | Impact / Business Value | Dependencies
46 | Yes | S8.1 | E8 | Roadmap Engine (System) | Roadmap Generation Engine (Based on Domain + Stack + Trends + Analysis) | Must-have | Core differentiator translating insights into action plan | E3, E4, E5, E7
| No | S8.2 | E8 | Roadmap Engine (System) | Milestone Definition (Skills, Projects, Outcomes) | Must-have | Structures learning into achievable stages | S8.1
| No | S8.3 | E8 | Roadmap Engine (System) | Task/Activity Definition within Milestones | Must-have | Converts milestones into executable steps | S8.2
| No | S8.4 | E8 | Roadmap Engine (System) | Roadmap Personalization (Based on Skill Gaps) | Must-have | Tailors roadmap per individual readiness | E3, S8.1
47 | Yes | S8.5 | E8 | Roadmap Engine (System) | Roadmap Visualization UI (Timeline / Step View) | Must-have | Improves clarity and engagement | S8.1
| No | S8.6 | E8 | Roadmap Engine (System) | Estimated Timeline per Milestone | Must-have | Sets realistic expectations and planning | S8.2
48 | Yes | S8.7 | E8 | Roadmap Engine (System) | Dynamic Roadmap Update (Based on Progress & Trends) | Must-have | Keeps roadmap relevant and adaptive | E7, E9
| No | S8.8 | E8 | Roadmap Engine (System) | Recommended Projects Mapping per Milestone | Must-have | Ensures practical application of learning | S8.2
| No | S8.9 | E8 | Roadmap Engine (System) | Skill-to-Milestone Mapping | Must-have | Tracks skill coverage across roadmap | E4, S8.2
| No | S8.10 | E8 | Roadmap Engine (System) | Roadmap Versioning (Track Changes Over Time) | Must-have | Maintains consistency and traceability | S8.1
| No | S8.11 | E8 | Roadmap Engine (System) | Roadmap Save / Activate Functionality | Must-have | Locks user journey for execution phase | S8.1
| No | S8.12 | E8 | Roadmap Engine (System) | Roadmap Regeneration Trigger (Manual / System-driven) | Must-have | Allows users to refresh path when needed | E3, E7
| No | S8.13 | E8 | Roadmap Engine (System) | Roadmap API Layer (For Integration with Execution Module) | Must-have | Enables seamless integration with execution tracking | S8.1
| No | S8.14 | E8 | Roadmap Engine (System) | Difficulty Level Classification (Beginner / Intermediate / Advanced) | Must-have | Aligns roadmap complexity with user level | E3
49 | Yes | S8.15 | E8 | Roadmap Engine (System) | Roadmap Summary View (High-Level Overview) | Must-have | Quick understanding before deep dive | S8.1
|  | Story ID | Feature ID / Epic ID | Feature / Epic | Feature / Function / Screen | Type (MoSCoW) / Labels | Impact / Business Value | Dependencies
50 | Yes | S9.1 | E9 | Roadmap Selection & Execution | Roadmap Selection (Choose from Generated Roadmap Options) | Must-have | Enables user commitment to a structured path | E8
| No | S9.2 | E9 | Roadmap Selection & Execution | Roadmap Activation (Lock Selected Roadmap) | Must-have | Prevents frequent switching and ensures focus | S9.1
| No | S9.3 | E9 | Roadmap Selection & Execution | Milestone Progress Tracking | Must-have | Tracks advancement across roadmap stages | S9.2
| No | S9.4 | E9 | Roadmap Selection & Execution | Task Progress Tracking (Mark Complete / In Progress) | Must-have | Drives execution discipline and engagement | S9.3
| No | S9.5 | E9 | Roadmap Selection & Execution | Task Detail View (Description, Expected Outcome, Resources) | Must-have | Provides clarity on what to execute | E8
| No | S9.6 | E9 | Roadmap Selection & Execution | Progress Dashboard (Overall % Completion) | Must-have | Motivates users through visible progress | S9.3
| No | S9.7 | E9 | Roadmap Selection & Execution | Milestone Completion Validation (Basic Rule-based Check) | Must-have | Ensures structured progression before moving ahead | S9.3
51 | Yes | S9.8 | E9 | Roadmap Selection & Execution | Task-to-Portfolio Linking (Convert Task → Portfolio Entry) | Must-have | Connects execution with portfolio building | E2
| No | S9.9 | E9 | Roadmap Selection & Execution | Resume/Pause Roadmap | Must-have | Allows flexibility without losing progress | S9.2
| No | S9.10 | E9 | Roadmap Selection & Execution | Reminder / Notification System (Pending Tasks / Milestones) | Must-have | Improves completion rates and engagement | S9.3
| No | S9.11 | E9 | Roadmap Selection & Execution | Activity Timeline (Track User Actions Over Time) | Must-have | Provides visibility into consistency and effort | S9.3
52 | Yes | S9.12 | E9 | Roadmap Selection & Execution | Progress Sync with Portfolio Analysis | Must-have | Updates job readiness score dynamically | E3
| No | S9.13 | E9 | Roadmap Selection & Execution | Unlock Next Milestone (Based on Completion Rules) | Must-have | Creates structured learning flow | S9.7
| No | S9.14 | E9 | Roadmap Selection & Execution | Manual Task Addition (User-defined Work) | Must-have | Allows flexibility beyond system-defined tasks | S9.4
53 | Yes | S9.15 | E9 | Roadmap Selection & Execution | Execution Summary View (Completed vs Pending Work) | Must-have | Helps users understand their journey status | S9.6
|  | Story ID | Feature ID / Epic ID | Feature / Epic | Feature / Function / Screen | Type (MoSCoW) / Labels | Impact / Business Value | Dependencies
54 | Yes | S7.1 | E7 | Trend Analysis Engine | Skill Extraction from Job Descriptions (NLP / Rule-based) | Must-have | Converts raw job data into structured skill signals | E6
55 | Yes | S7.2 | E7 | Trend Analysis Engine | Role Extraction from Job Data | Must-have | Identifies demand by job roles | E6
56 | Yes | S7.3 | E7 | Trend Analysis Engine | Skill Frequency Aggregation Engine | Must-have | Measures demand intensity of each skill | S10.1
57 | Yes | S7.4 | E7 | Trend Analysis Engine | Domain Mapping (Skills → Domains) | Must-have | Connects market demand to platform domains | E4, S10.3
| No | S7.5 | E7 | Trend Analysis Engine | Time-Based Trend Window (3 / 6 / 12 Months Configurable) | Must-have | Enables trend relevance based on time horizon | S10.3
| No | S7.6 | E7 | Trend Analysis Engine | Trend Weightage Calculation Engine | Must-have | Assigns importance score to skills/domains | S10.3, S10.5
58 | Yes | S7.7 | E7 | Trend Analysis Engine | Skill Demand Ranking Engine | Must-have | Prioritizes high-demand skills | S10.6
59 | Yes | S7.8 | E7 | Trend Analysis Engine | Domain Popularity Index Calculation | Must-have | Shows growth/decline of domains | S10.4, S10.6
60 | Yes | S7.9 | E7 | Trend Analysis Engine | Trend Dashboard (Skills, Roles, Domains Visualization) | Must-have | Makes insights accessible to users | S10.6
61 | Yes | S7.10 | E7 | Trend Analysis Engine | Trend Data Refresh Scheduler (Daily / Weekly Jobs). Every job input may change it. | Must-have | Keeps insights up-to-date | E6
| No | S7.11 | E7 | Trend Analysis Engine | Trend API Layer (Expose Data to Other Modules) | Must-have | Enables reuse across platform (E3, E5, E8) | S10.6
| No | S7.12 | E7 | Trend Analysis Engine | Trend Integration with Domain Engine | Must-have | Keeps domain definitions aligned with market | E4
| No | S7.13 | E7 | Trend Analysis Engine | Trend Integration with Stack Recommendation | Must-have | Improves accuracy of stack suggestions | E5
62 | Yes | S7.14 | E7 | Trend Analysis Engine | Trend Integration with Portfolio Analysis | Must-have | Enables market-aligned job readiness scoring | E3
63 | Yes | S7.15 | E7 | Trend Analysis Engine | Trend Integration with Roadmap Engine | Must-have | Ensures roadmap reflects current demand | E8
| No | S7.16 | E7 | Trend Analysis Engine | Emerging Skills Detection (Spike Detection Logic) | Must-have | Identifies early opportunities for students | S10.6
| No | S7.17 | E7 | Trend Analysis Engine | Declining Skills Detection | Must-have | Prevents students from investing in outdated skills | S10.6
| No | S7.18 | E7 | Trend Analysis Engine | Trend Alerts & Notifications | Must-have | Drives proactive student action | S10.16
| No | S7.19 | E7 | Trend Analysis Engine | Manual Override / Admin Adjustment of Trends | Must-have | Allows control over anomalies or bias in data | S10.6
| No | S7.20 | E7 | Trend Analysis Engine | Trend Confidence Score (Data Quality Indicator) | Must-have | Ensures trust in insights generated | S10.6

## Sheet2
Story ID | Feature ID | Feature / Epic | Feature / Function / Screen | Type | Impact | Dependencies | Screen / Background Logic
S1.1 | E1 | Student Registration | Student Sign-up (Email) | Must-have | User onboarding entry point | - | Screen
S1.2 | E1 | Student Registration | Profile Setup (Basic Info) | Must-have | Structured identity creation | S1.1 | Screen
S1.3 | E1 | Student Registration | Skills & Interests Selection | Must-have | Enables personalization | S1.2 | Screen
S1.4 | E1 | Student Registration | Career Goal Selection | Must-have | Drives roadmap + recommendations | S1.2 | Screen
S1.5 | E1 | Student Registration | Profile Dashboard | Must-have | Central control for user | S1.2 | Screen
Story ID | Feature ID | Feature / Epic | Feature / Function / Screen | Type | Impact | Dependencies | Screen / Background Logic
S2.1 | E2 | Portfolio | Add Project | Must-have | Core portfolio creation | E1 | Screen
S2.2 | E2 | Portfolio | Add External Links | Must-have | Proof of work | S2.1 | Screen
S2.3 | E2 | Portfolio | Upload Media | Must-have | Visual credibility | S2.1 | Screen
S2.4 | E2 | Portfolio | Add Skills & Certifications | Must-have | Profile strength | E1 | Screen
S2.5 | E2 | Portfolio | Tag Project to Stack/Roadmap | Must-have | Enables analysis | E5 | Background Logic
S2.6 | E2 | Portfolio | Edit/Delete Entries | Must-have | Data control | S2.1 | Screen
S2.8 | E2 | Portfolio | Project Detail View | Must-have | Structured display | S2.1 | Screen
S2.10 | E2 | Portfolio | Portfolio Completeness % | Must-have | Improves engagement | S2.7 | Background Logic
Story ID | Feature ID | Feature / Epic | Feature / Function / Screen | Type | Impact | Dependencies | Screen / Background Logic
S3.1 | E3 | Analysis | Portfolio Data Aggregation | Must-have | Data consolidation | E2 | Background Logic
S3.2 | E3 | Analysis | Skill Mapping to Stack | Must-have | Alignment | E2, E5 | Background Logic
S3.3 | E3 | Analysis | Job Readiness Score Engine | Must-have | Core metric | S3.1, S3.2 | Background Logic
S3.4 | E3 | Analysis | Weightage Configuration | Must-have | Flexible scoring | S3.3 | Background Logic
S3.6 | E3 | Analysis | Strength Analysis | Must-have | Confidence boost | S3.2 | Background Logic
S3.8 | E3 | Analysis | Trend Alignment Check | Must-have | Market relevance | E7 | Background Logic
S3.9 | E3 | Analysis | Readiness Dashboard | Must-have | Visualization | S3.3 | Screen
S3.10 | E3 | Analysis | Insights Panel | Must-have | Transparency | S3.9 | Screen
S3.13 | E3 | Analysis | Historical Tracking | Must-have | Growth tracking | S3.3 | Background Logic
S3.14 | E3 | Analysis | Readiness Classification | Must-have | Simplified output | S3.3 | Background Logic
Story ID | Feature ID | Feature / Epic | Feature / Function / Screen | Type | Impact | Dependencies | Screen / Background Logic
S4.1 | E4 | Domain | Domain Master Setup | Must-have | Foundation | - | Background Logic
S4.2 | E4 | Domain | Domain Categorization | Must-have | Scalability | S4.1 | Background Logic
S4.3 | E4 | Domain | Skill Mapping | Must-have | Structure | S4.1 | Background Logic
S4.4 | E4 | Domain | Role Mapping | Must-have | Job linkage | S4.1 | Background Logic
S4.5 | E4 | Domain | Domain Description | Must-have | Understanding | S4.1 | Screen
S4.6 | E4 | Domain | Domain Selection UI | Must-have | Personalization | E1 | Screen
S4.7 | E4 | Domain | Domain Detail View | Must-have | Decision support | S4.3 | Screen
S4.8 | E4 | Domain | Multi-domain Selection | Must-have | Flexibility | S4.6 | Screen
S4.9 | E4 | Domain | Domain Prioritization | Must-have | Focus | S4.8 | Screen
S4.10 | E4 | Domain | Domain Change Flow | Must-have | Flexibility | S4.6 | Screen
S4.11 | E4 | Domain | Domain-Trend Mapping | Must-have | Dynamic alignment | E7 | Background Logic
S4.12 | E4 | Domain | Domain-Roadmap Mapping | Must-have | Roadmap base | E8 | Background Logic
S4.13 | E4 | Domain | Domain Visibility Control | Must-have | Admin control | S4.1 | Background Logic
S4.14 | E4 | Domain | Domain Analytics | Must-have | Optimization | E1, E7 | Background Logic
Story ID | Feature ID | Feature / Epic | Feature / Function / Screen | Type | Impact | Dependencies | Screen / Background Logic
S5.2 | E5 | Stack | Stack Detail View | Must-have | Clarity | S5.1 | Screen
S5.3 | E5 | Stack | Stack Selection | Must-have | Focus | S5.1 | Screen
S5.7 | E5 | Stack | Stack Tracking | Must-have | Progress | S5.6 | Background Logic
S5.11 | E5 | Stack | Stack-Roadmap Mapping | Must-have | Execution link | E8 | Background Logic
Story ID | Feature ID | Feature / Epic | Feature / Function / Screen | Type | Impact | Dependencies | Screen / Background Logic
S6.5 | E6 | Jobs | Job Repository | Must-have | Data base | S6.2 | Background Logic
S6.7 | E6 | Jobs | Job Detail View | Must-have | Info clarity | S6.6 | Screen
S6.8 | E6 | Jobs | Job Filters | Must-have | Usability | S6.6 | Screen
S6.14 | E6 | Jobs | Feed → Trend Integration | Must-have | Data pipeline | E7 | Background Logic
Story ID | Feature ID | Feature / Epic | Feature / Function / Screen | Type | Impact | Dependencies | Screen / Background Logic
S7.1 | E7 | Trend | Skill Extraction | Must-have | Data structuring | E6 | Background Logic
S7.2 | E7 | Trend | Role Extraction | Must-have | Role demand | E6 | Background Logic
S7.3 | E7 | Trend | Frequency Aggregation | Must-have | Demand intensity | S7.1 | Background Logic
S7.4 | E7 | Trend | Domain Mapping | Must-have | Domain linkage | E4 | Background Logic
S7.7 | E7 | Trend | Skill Ranking | Must-have | Prioritization | S7.6 | Background Logic
S7.8 | E7 | Trend | Domain Popularity | Must-have | Insight | S7.4 | Background Logic
S7.9 | E7 | Trend | Trend Dashboard | Must-have | Visibility | S7.6 | Screen
S7.10 | E7 | Trend | Scheduler | Must-have | Fresh data | E6 | Background Logic
S7.14 | E7 | Trend | Portfolio Integration | Must-have | Alignment | E3 | Background Logic
S7.15 | E7 | Trend | Roadmap Integration | Must-have | Planning | E8 | Background Logic
Story ID | Feature ID | Feature / Epic | Feature / Function / Screen | Type | Impact | Dependencies | Screen / Background Logic
S8.1 | E8 | Roadmap | Roadmap Engine | Must-have | Core planning | E3, E4, E5, E7 | Background Logic
S8.5 | E8 | Roadmap | Visualization UI | Must-have | Engagement | S8.1 | Screen
S8.7 | E8 | Roadmap | Dynamic Update | Must-have | Adaptability | E7, E9 | Background Logic
S8.15 | E8 | Roadmap | Summary View | Must-have | Quick view | S8.1 | Screen
Story ID | Feature ID | Feature / Epic | Feature / Function / Screen | Type | Impact | Dependencies | Screen / Background Logic
S9.1 | E9 | Execution | Roadmap Selection | Must-have | Commitment | E8 | Screen
S9.8 | E9 | Execution | Task → Portfolio | Must-have | Loop closure | E2 | Background Logic
S9.12 | E9 | Execution | Progress Sync | Must-have | Real-time score | E3 | Background Logic
S9.15 | E9 | Execution | Execution Summary | Must-have | Visibility | S9.6 | Screen